## Sheet1
Location | Project | Description | Total Cost | Status
Bolton HS | Athletics | Outdoor Lighting (softball, baseball, soccer) | 730000 | Scope being developed. Expected Board Approval October (ESSER funded projects to bid first)
Bolton HS | Electric | LED Lighting Upgrade-Gym | 35000 | Scope being developed. Expected Board Approval October (ESSER funded projects to bid first)
Booker T Washington HS | Roof | Roof Replacement | 6496500 | Project initiation form, scope, and budget codes submitted. Working with Procurement on RFP. OEO meeting 8/11/24. Target Board approval in September.
Booker T Washington HS | Windows | Window Replacement | 5431500 | Project initiation form, scope, and budget codes submitted. Working with Procurement on RFP. OEO meeting 8/11/24. Target Board approval in September.
Booker T Washington HS | Electric | LED Lighting Upgrade-Gym | 35000 | Scope being developed. Expected Board Approval October (ESSER funded projects to bid first)
Cordova HS | Athletics | Outdoor Lighting (softball, baseball, soccer) | 735000 | Scope being developed. Expected Board Approval October (ESSER funded projects to bid first)
Cordova HS | Paving | Entire Lot | 1000000 | Scope being developed. Expected Board Approval October (ESSER funded projects to bid first)
Cordova MS | Paving | Entire Lot | 600000 | Scope being developed. Expected Board Approval October (ESSER funded projects to bid first)
Craigmont HS | Electric | LED Lighting Upgrade-Gym | 35000 | Scope being developed. Expected Board Approval October (ESSER funded projects to bid first)
Craigmont MS | Electric | LED Lighting Upgrade-Gym | 35000 | Scope being developed. Expected Board Approval October (ESSER funded projects to bid first)
Cromwell ES | HVAC | Replace Chiller, Boiler, Pumps, RTU, UV, Controls | 3165000 | Project initiation form, scope, and budget codes submitted. Working with Procurement on RFP. OEO meeting 8/11/24. Target Board approval in September.
Crump Stadium | Athletics | Track resurfacing | 600000 | Scope being developed. Expected Board Approval October (ESSER funded projects to bid first)
Dunbar ES | Windows | Window Replacement | 2343000 | Project initiation form, scope, and budget codes submitted. Working with Procurement on RFP. OEO meeting 8/11/24. Target Board approval in September.
East HS | Windows | Window Replacement | 6390000 | Project initiation form, scope, and budget codes submitted. Working with Procurement on RFP. OEO meeting 8/11/24. Target Board approval in September.
Egypt ES | HVAC | Replace Chiller, Boiler, UV, RTU, Pumps, Controls | 5802500 | Project initiation form, scope, and budget codes submitted. Working with Procurement on RFP. OEO meeting 8/11/24. Target Board approval in September.
Ford Road ES | HVAC | Chiller(2), CT(2), Boiler(2), RTU, Controls | 2110000 | Project initiation form, scope, and budget codes submitted. Working with Procurement on RFP. OEO meeting 8/11/24. Target Board approval in September.
Fox Meadows ES | Roof | Roof Replacement | 3195000 | Project initiation form, scope, and budget codes submitted. Working with Procurement on RFP. OEO meeting 8/11/24. Target Board approval in September.
Frayser-Corning ES | Foundation | Repair NW Exterior Stairwell | 315000 | Scope being developed. Expected Board Approval October (ESSER funded projects to bid first)
Geeter K8 | Roof | Roof Replacement | 2662500 | Project initiation form, scope, and budget codes submitted. Working with Procurement on RFP. OEO meeting 8/11/24. Target Board approval in September.
Georgian Hills MS | Electric | LED Lighting Upgrade-Gym | 35000 | Scope being developed. Expected Board Approval October (ESSER funded projects to bid first)
Germantown HS | Fire/Life Safety | Replace Fire Detection System | 1500000 | Scope being developed. Expected Board Approval October (ESSER funded projects to bid first)
Gordon Alternative | HVAC | Water cooled chiller, CT, Boiler, Pumps, Controls | 1371500 | Project initiation form, scope, and budget codes submitted. Working with Procurement on RFP. OEO meeting 8/11/24. Target Board approval in September.
Grandview MS | Roof | Roof Replacement | 2236500 | Project initiation form, scope, and budget codes submitted. Working with Procurement on RFP. OEO meeting 8/11/24. Target Board approval in September.
Hollywood Admin. | Fire/Life Safety | Replace Fire Detection System | 600000 | Scope being developed. Expected Board Approval October (ESSER funded projects to bid first)
Holmes Rd. ES | HVAC | Replace Chiller, Boiler, Cooling Tower and Pumps, Controls | 1688000 | Project initiation form, scope, and budget codes submitted. Working with Procurement on RFP. OEO meeting 8/11/24. Target Board approval in September.
Idlewild ES | Plumbing | Reroute Sewer Line to Gym | 319500 | Architect design contract pending approval internal approval routing process; Project will be bid once design received.
Invictus Academy (Airways) | Windows | Window Replacement | 5112000 | Project initiation form, scope, and budget codes submitted. Working with Procurement on RFP. OEO meeting 8/11/24. Target Board approval in September.
Kingsbury HS | HVAC | Replace SCUVs, Chiller, AHU, RTU, Controls | 5169500 | Project initiation form, scope, and budget codes submitted. Working with Procurement on RFP. OEO meeting 8/11/24. Target Board approval in September.
Kingsbury MS/HS | Athletics | Outdoor Lighting (softball, baseball, soccer) | 300000 | Scope being developed. Expected Board Approval October (ESSER funded projects to bid first)
Kingsbury MS/HS | Plumbing | Replace Gas Line | 3500000 | Scope being developed. Expected Board Approval October (ESSER funded projects to bid first)
Kirby HS | Electric | LED Lighting Upgrade-Gym | 35000 | Scope being developed. Expected Board Approval October (ESSER funded projects to bid first)
Norris Achievement Academy | HVAC | Replace Chiller and Controls | 263750 | Project initiation form, scope, and budget codes submitted. Working with Procurement on RFP. OEO meeting 8/11/24. Target Board approval in September.
Norris Achievement Academy | Windows | Window Replacement | 1917000 | Project initiation form, scope, and budget codes submitted. Working with Procurement on RFP. OEO meeting 8/11/24. Target Board approval in September.
Oakshire ES | HVAC | Chiller(2), Boiler(2), Pumps, UV, Controls | 5802500 | Project initiation form, scope, and budget codes submitted. Working with Procurement on RFP. OEO meeting 8/11/24. Target Board approval in September.
Overton HS | Paving | Entire Lot | 600000 | Scope being developed. Expected Board Approval October (ESSER funded projects to bid first)
Raileigh Egypt MS | HVAC | Replace Chiller, CT, Controls | 1582500 | Project initiation form, scope, and budget codes submitted. Working with Procurement on RFP. OEO meeting 8/11/24. Target Board approval in September.
Raleigh Bartlett ES | Roof | Roof Replacement | 1065000 | Project initiation form, scope, and budget codes submitted. Working with Procurement on RFP. OEO meeting 8/11/24. Target Board approval in September.
Ridgeway HS | Paving | 60% of Lot | 600000 | Scope being developed. Expected Board Approval October (ESSER funded projects to bid first)
Ridgeway HS | Electric | LED Lighting Upgrade-Gym | 35000 | Scope being developed. Expected Board Approval October (ESSER funded projects to bid first)
Rozelle ES | Foundation | Repair Lower Floor Walls (east end) | 157500 | Scope being developed. Expected Board Approval October (ESSER funded projects to bid first)
Shady Grove PK | Roof | Roof Replacement | 1065000 | Project initiation form, scope, and budget codes submitted. Working with Procurement on RFP. OEO meeting 8/11/24. Target Board approval in September.
Sheffield HS | Fire/Life Safety | Replace Fire Detection System | 700000 | Scope being developed. Expected Board Approval October (ESSER funded projects to bid first)
Sheffield HS | Roof | Roof Replacement | 6922500 | Project initiation form, scope, and budget codes submitted. Working with Procurement on RFP. OEO meeting 8/11/24. Target Board approval in September.
Sherwood MS | Foundation | Repair Library Wing Walls | 525000 | Scope being developed. Expected Board Approval October (ESSER funded projects to bid first)
Shrine School | HVAC | Replace Boilers, Pumps, Chillers, Controls | 844000 | Project initiation form, scope, and budget codes submitted. Working with Procurement on RFP. OEO meeting 8/11/24. Target Board approval in September.
Snowden K8 | Paving | Entire Lot | 200000 | Scope being developed. Expected Board Approval October (ESSER funded projects to bid first)
Southwind HS | Athletics | Outdoor Lighting (softball, baseball, soccer) | 735000 | Scope being developed. Expected Board Approval October (ESSER funded projects to bid first)
Southwind HS | Electric | LED Lighting Upgrade-Gym | 35000 | Scope being developed. Expected Board Approval October (ESSER funded projects to bid first)
Springdale ES | HVAC | UV, RTU, AHU, Boiler, Pump, Chiller, Controls | 8440000 | Project initiation form, scope, and budget codes submitted. Working with Procurement on RFP. OEO meeting 8/11/24. Target Board approval in September.
TLA Admin | Roof | Roof Replacement | 1597500 | Project initiation form, scope, and budget codes submitted. Working with Procurement on RFP. OEO meeting 8/11/24. Target Board approval in September.
White Station HS | Electric | LED Lighting Upgrade-Gym | 35000 | Scope being developed. Expected Board Approval October (ESSER funded projects to bid first)
Wooddale HS | Electric | LED Lighting Upgrade-Gym | 35000 | Scope being developed. Expected Board Approval October (ESSER funded projects to bid first)